CRITICAL TASK ITEM (CTI)

Proposal and Objective Scoring Intake Package

V4.1 Prototype Submission Template

| CTI Title | Mock CTI — Citation Longitude Fuel Quantity Indication Intermittency |
| --- | --- |
| Model / Program | Citation Longitude (Model 700) |
| Requesting Organization | Customer Service Engineering / Avionics |
| Originator | Jordan Lee (fictional), Senior Avionics Engineer |
| Proposed Champion | Morgan Reyes (fictional), Director — Citation Product Support |
| Submission Date | 09/11/2026 |
| Need-By Date | 03/31/2027 |
| Document Revision | A - Initial Submission |

PURPOSE: Capture the factual, schedule, business-case, impact, and evidence information required for automated CTI qualification, objective scoring, confidence assessment, and ranking. The submitter does not assign a score or rank.

# 1. Submission Control

| Package Status | ☐ Draft ☒ Submitted ☐ Returned for Information ☐ Validated |
| --- | --- |
| Requested Classification | ☒ Discretionary ☐ Safety / Regulatory ☐ SLT / External Commitment |
| Requested Driver | ☒ Quality/Reliability ☐ Supply Chain ☐ Production Support ☐ Safety ☐ Certification Mandate ☒ Customer Service ☐ Marketability ☐ Obsolescence |
| Current Phase | ☐ Phase 1 - Issue Identification ☒ Phase 2 - Business Case |

# 2. Executive Summary

PROBLEM STATEMENT

During a mock 12-month review, Customer Service Engineering identified 18 intermittent left- or right-main fuel quantity indication events across 14 Citation Longitude aircraft. Most events cleared after power cycling, but six produced dispatch delays and two required overnight troubleshooting. Review of fictional service records E-01 through E-03 indicates repeat removals of probes and signal-conditioning modules without a consistent root-cause isolation path. The current maintenance procedure does not capture connector pin-fit degradation and transient data-bus faults early enough, resulting in repeat troubleshooting and avoidable aircraft downtime.

DESIRED OUTCOME

Develop, validate, and release an improved troubleshooting procedure and targeted connector inspection criteria by 03/31/2027. Within 12 months of release, reduce repeat fuel-quantity indication events by at least 60%, cut average troubleshooting time from 11.5 to 5 labor-hours, and reduce related dispatch delays from six to two or fewer per year.

CONSEQUENCE OF NO ACTION

If no action is taken, the modeled fleet is expected to continue experiencing approximately 18 events annually, including six dispatch delays, two AOG events, and recurring no-fault-found removals. The mock five-year exposure is estimated at $2.15 million in labor, expedited parts, warranty concessions, and customer downtime. Continued recurrence may also reduce customer confidence in dispatch reliability and increase service-center workload.

# 3. CTI Qualification

## Qualification Indicators

☐  Externally imposed regulatory or certification deadline

☐  Qualifying safety / COS hazard evidence

☐  Obsolescence requiring substantive engineering effort

☒  Engineering focal labor exceeds the applicable CTI threshold

☒  Cross-functional issue requiring Core Team awareness and prioritization

☒  Not a unit-specific change, fast engineering item, or non-ECR corrective action

QUALIFICATION RATIONALE

This issue qualifies as a mock CTI because the modeled corrective action requires approximately 1,480 engineering hours across seven functions, affects multiple aircraft in the active fleet, and requires coordinated design, maintainability, publications, validation, and service implementation. The issue cannot be resolved as a unit-specific change because the proposed solution changes fleet-level troubleshooting instructions and may introduce connector inspection criteria. Supporting mock evidence is recorded as E-01 through E-06.

# 4. Scope and Business Case

SCOPE

In scope: Citation Longitude aircraft serial numbers 700-0001 through 700-0158 with the baseline fuel quantity indication architecture; left and right main tank indication channels; aircraft wiring, connectors, fuel probes, signal-conditioning modules, maintenance diagnostics, and applicable maintenance publications. Organizations include Avionics Engineering, Electrical Systems, Customer Service Engineering, Reliability, Quality, Technical Publications, and Program Management. Excluded: fuel leaks, refueling components, auxiliary tank systems, aircraft with unrelated display failures, and any production configuration introduced after serial 700-0158 unless later approved through change control.

BUSINESS CASE

The proposed CTI is expected to prevent repeat troubleshooting, reduce AOG exposure, and improve dispatch reliability with a limited documentation and inspection change. The fictional business model estimates $2.15 million in gross five-year avoided cost against $0.62 million in nonrecurring engineering and implementation cost, yielding a $1.53 million net benefit. Action is needed now to complete validation before the 2027 spring heavy-maintenance cycle and to incorporate revised instructions into the next planned publications release.

| Affected Model Families | 1 — Citation Longitude |
| --- | --- |
| Affected Aircraft | 14 aircraft with recorded events |
| Applicable Active Fleet | 132 aircraft |
| Functions with Deliverables | 7 — Avionics, Electrical, Customer Service, Reliability, Quality, Technical Publications, Program Management |
| Estimated Engineering Lead Time | 194 calendar days |
| Estimated Engineering Labor | 1,480 hours |
| 5-Year Net Benefit / Avoided Cost | $1.53M net benefit; fictional finance model E-05 |

# 5. Objective Impact Data

| Objective Input | Value | Measurement Period / Basis | Evidence ID |
| --- | --- | --- | --- |
| Annual AOG events | 2 | Rolling 12 months ending 08/31/2026 | E-01 |
| Annual prevented deliveries | 0 | Rolling 12 months ending 08/31/2026 | E-02 |
| Annual delivery delays | 6 | Rolling 12 months ending 08/31/2026 | E-02 |
| Annual line interruptions | 3 | Rolling 12 months ending 08/31/2026 | E-03 |
| Annual repeat rework events | 11 | Rolling 12 months ending 08/31/2026 | E-01 |
| Affected fleet percentage | 10.6% | 14 event aircraft / 132 active aircraft | E-04 |
| Service consequence | Dispatch delay; occasional AOG | Service-case severity review | E-02 |
| Lifecycle breadth | In-service maintenance and publications | Operations, maintenance, reliability, support | E-06 |
| Customer commitment / escalation | No external commitment; recurring customer escalations | 4 escalated cases in review period | E-02 |

# 6. Schedule and Milestones

| Need-By Date | 03/31/2027 — next planned maintenance publication release |
| --- | --- |
| Target Completion Date | 03/15/2027 |
| Estimated Implementation Lead Time | 194 calendar days |
| Schedule Margin | 16 calendar days |

| Milestone | Owner | Target Date | Completion Evidence |
| --- | --- | --- | --- |
| Approve problem statement and scope | Program Management | 09/30/2026 | Core Team minutes |
| Complete root-cause confirmation testing | Avionics Engineering | 11/20/2026 | Test report E-07 |
| Release preliminary technical solution | Electrical Systems | 12/18/2026 | Design review record |
| Validate maintenance procedure on representative aircraft | Customer Service Engineering | 01/29/2027 | Validation report E-08 |
| Approve publication change package | Technical Publications | 02/26/2027 | Approved change package |
| Publish revised instructions and service communication | Customer Service | 03/15/2027 | Released publication revision |

# 7. Execution Readiness

## Documented Readiness Items

☒  Named accountable owner

☒  Approved problem statement and scope

☒  Business case completed

☒  Engineering estimate completed

☒  Required functions identified

☒  Need-by and target dates validated

☒  Initial technical approach identified

☒  Funding or resource source identified

RESOURCE AND TEAM PLAN

Program Management will provide a 0.25 FTE project lead through release. Avionics Engineering will lead fault recreation and diagnostic logic (520 hours); Electrical Systems will support connector and wiring assessment (300 hours); Customer Service Engineering will provide aircraft access and validation (260 hours); Reliability and Quality will analyze event trends and verify corrective-action effectiveness (180 hours); Technical Publications will revise maintenance content (160 hours); and Finance/Contracts support will validate cost assumptions (60 hours). Key dependencies are access to one representative aircraft, availability of returned hardware, and coordination with the March 2027 publication cycle. The mock funding source is the Citation sustaining-engineering budget.

# 8. Evidence Register

| Evidence ID | Document / Record Title | Type | Owner | Location / Link |
| --- | --- | --- | --- | --- |
| E-01 | Fictional Fuel Quantity Service Event Log | Reliability data | Reliability Engineering | Mock CTI repository |
| E-02 | Fictional Customer Escalation Summary | Service cases | Customer Service | Mock CTI repository |
| E-03 | Fictional Production and Service Interruption Extract | Operations data | Quality Analytics | Mock CTI repository |
| E-04 | Fictional Active Fleet Configuration Report | Fleet data | Program Analytics | Mock CTI repository |
| E-05 | Fictional Five-Year Cost Avoidance Model | Finance model | Program Finance | Mock CTI repository |
| E-06 | Fictional Engineering Estimate and Work Breakdown | Estimate | Avionics Engineering | Mock CTI repository |
| E-07 | Planned Root-Cause Confirmation Test Report | Test report | Avionics Engineering | Pending — mock deliverable |
| E-08 | Planned Maintenance Procedure Validation Report | Validation | Customer Service Engineering | Pending — mock deliverable |

# 9. Mandatory Classification Evidence

SAFETY / REGULATORY / SLT / EXTERNAL COMMITMENT BASIS

Not applicable. This mock submission requests a discretionary Quality/Reliability and Customer Service classification. No safety, regulatory, SLT, or externally committed deadline is claimed.

# 10. Originator Certification

| Originator Signature / Electronic Acknowledgment | Date |
| --- | --- |
| Jordan Lee (fictional) — electronic acknowledgment for mock testing | 09/11/2026 |

I certify that the factual inputs are accurate to the best of my knowledge, that cited evidence is available for review, and that I have not assigned or altered the automated score or rank.

# 11. System and Reviewer Use Only

| Validation Result | ☐ Complete ☐ Returned for Information ☐ Rejected |
| --- | --- |
| System Qualification | [Calculated] |
| Automatic Priority Tier | [Calculated] |
| Objective Priority Score | [Calculated] |
| Confidence Score | [Calculated] |
| Company Rank | [Calculated] |
| Model Rank | [Calculated] |
| Reviewer | [Name / date] |

VALIDATION NOTES

Document missing information, evidence limitations, corrections, or reviewer disposition.

# 12. Submission Checklist

## Required Before Submission

☒  All required identification fields completed

☒  Business case and scope completed

☒  Need-by date and implementation lead time provided

☒  Objective impact quantities provided

☒  Evidence register completed

☒  Mandatory classification supported, if requested (not applicable)

☒  Milestone schedule included

☒  Originator certification completed